## Worksheet
NOTES: Project Deliverables and Moderate Effort Tracking
Milestone | Task ID | Task Description | Start Date | Completion Date | Team Member | Activity | Status | Effort (Hours) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
[9 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
MILESTONE 1: DOCUMENT INGESTION & INDEXING (COMPLETED 08 JAN)
M1 | T-01 | Setup Vector Database & Ingestion Logic | 01/01/2026 | 04/01/2026 | Monika S | Backend | 3- Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M1 | T-02 | Document Text Splitting & Embedding Generation | 04/01/2026 | 08/01/2026 | Monika S | Logic | 3- Completed | 10 | 0 | 0 | 0 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MILESTONE 2: RAG PIPELINE DEVELOPMENT (COMPLETED 18 JAN)
M2 | T-03 | Integrate Retrieval Mechanism with LLM API | 09/01/2026 | 14/01/2026 | Monika S | Integration | 3- Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0
M2 | T-04 | Answer Synthesis & Source Citation Logic | 14/01/2026 | 18/01/2026 | Monika S | Logic | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | 4 | 0 | 0
MILESTONE 3: CONVERSATIONAL UI & DIALOGUE (COMPLETED 28 JAN)
M3 | T-05 | Develop Frontend Chat Interface (Glassmorphism) | 19/01/2026 | 24/01/2026 | Monika S | Frontend | 3- Completed | 12 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
M3 | T-06 | Multi-turn Conversation & Follow-up Logic | 24/01/2026 | 28/01/2026 | Monika S | Dialogue | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 0
MILESTONE 4: DEPLOYMENT & EVALUATION (COMPLETED 10 FEB)
M4 | T-07 | Vercel Deployment & Runtime Optimization | 29/01/2026 | 05/02/2026 | Monika S | Deploy | 3- Completed | 14 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M4 | T-08 | Final Performance & Accuracy Evaluation | 05/02/2026 | 10/02/2026 | Monika S | Eval | 3- Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0