## Worksheet
Submitted Date | Description | Detected Milestone | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
03/01/2026 | Vector embedding generation failing for large text chunks | Milestone 1 | Monika S | Functional | Adjusted text splitter chunk size and added overlap for context. | 05/01/2026 | Closed | Stable embeddings
12/01/2026 | RAG model citing incorrect page numbers | Milestone 2 | Monika S | Data | Updated metadata extraction to properly map chunks to page indices. | 15/01/2026 | Closed | Citations verified
16/01/2026 | Prisma SQL connection hanging during RAG retrieval | Milestone 2 | Monika S | Functional | Implemented connection timeout and started refactor for Zero-DB. | 18/01/2026 | Closed | Resolved by architecture shift
22/01/2026 | Chat interface not scrolling to latest message | Milestone 3 | Monika S | UI | Added scrollIntoView trigger to ChatInterface.tsx component. | 24/01/2026 | Closed | UI scrolling smooth
26/01/2026 | Follow-up questions losing context of previous turn | Milestone 3 | Monika S | Logic | Updated Dialogue Manager to correctly pass thread history to LLM. | 28/01/2026 | Closed | Context working
02/02/2026 | Vercel Deployment failing on 'prisma generate' | Milestone 4 | Monika S | Deploy | Completely removed Prisma dependencies and switched to direct buffer RAG. | 05/02/2026 | Closed | Build successful
08/02/2026 | Final evaluation shows high latency on mobile devices | Milestone 4 | Monika S | Perf | Optimized client-side bundle size and CSS purging. | 10/02/2026 | Closed | Latency under 2s